## 2ADP001
NextFlex
REPORTING GROUP - TYPE A | ADP
SEQUENCE | 2ADP001
ROLLUP # | 1001
PROJECT NAME | Strategic Innovation Project Ph2
TECHNICAL POINT OF CONTACT | Aman S Gahoonia
PROJECT TYPE | ADP-Tech, ADP-Tech Subk
SERVICE | Other DOD
COLOR OF MONEY
ACRN | AC
AVAILABLE FUNDS | -271000000
|  | FYE 9/30/2020 |  |  |  | FYE 9/30/2021 |  |  |  | FYE 9/30/2022 |  |  |  | FYE 9/30/2023 |  |  |  | FYE 9/30/2024 |  |  |  | FYE 9/30/2025 |  |  |  | FYE 9/30/2026 |  |  |  | Grand Total
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ACTUALS | Labor Hours statistical account
| Labor Cost 5001 | FYE 9/30/2020 Q4: 26427.52; FYE 9/30/2021 Q4: 324777.02; FYE 9/30/2022 Q4: 117378.33
| Fringe 5990 | FYE 9/30/2020 Q4: 10988.56; FYE 9/30/2021 Q4: 128189.49; FYE 9/30/2022 Q4: 50378.83
Travel 5004
| Subcontracting 5005 | FYE 9/30/2020 Q4: 1863318.86; FYE 9/30/2021 Q4: 22353275.44; FYE 9/30/2022 Q4: 715405.39
| Consulting 5002 | FYE 9/30/2021 Q4: 24118.05; FYE 9/30/2022 Q4: 24045
Equipment 5010
| Equipment 5008 | FYE 9/30/2021 Q4: 520904.67; FYE 9/30/2022 Q4: 93165.06
| Other Direct Costs 5009 | FYE 9/30/2021 Q4: 59857.85; FYE 9/30/2022 Q4: 95947.15
| Material 5003 | FYE 9/30/2021 Q4: 55369.72; FYE 9/30/2022 Q4: 45630.26
| Sub K Overhead 5992 | FYE 9/30/2022 Q4: 18743.62
Sub K Overhead 5993
| G&A 5991 | FYE 9/30/2020 Q4: 12652.3; FYE 9/30/2021 Q4: 607236.18; FYE 9/30/2022 Q4: 550839.68
ACTUALS Total
BUDGETED | Labor Hours statistical account
| Labor Cost 5001 | FYE 9/30/2020 Q4: 123790.6; FYE 9/30/2021 Q1: 123790.6; FYE 9/30/2021 Q2: 123790.6; FYE 9/30/2021 Q3: 123790.6; FYE 9/30/2021 Q4: 123790.6; FYE 9/30/2022 Q1: 123790.6; FYE 9/30/2022 Q2: 123790.6; FYE 9/30/2022 Q3: 123790.6; FYE 9/30/2022 Q4: 123790.6; FYE 9/30/2023 Q1: 123790.6
| Fringe 5990 | FYE 9/30/2020 Q4: 51472.13; FYE 9/30/2021 Q1: 51472.13; FYE 9/30/2021 Q2: 51472.13; FYE 9/30/2021 Q3: 51472.13; FYE 9/30/2021 Q4: 51472.13; FYE 9/30/2022 Q1: 51472.13; FYE 9/30/2022 Q2: 51472.13; FYE 9/30/2022 Q3: 51472.13; FYE 9/30/2022 Q4: 51472.13; FYE 9/30/2023 Q1: 51472.13
Travel 5004
| Subcontracting 5005 | FYE 9/30/2020 Q4: 2493200; FYE 9/30/2021 Q1: 2493200; FYE 9/30/2021 Q2: 2493200; FYE 9/30/2021 Q3: 2493200; FYE 9/30/2021 Q4: 2493200; FYE 9/30/2022 Q1: 2493200; FYE 9/30/2022 Q2: 2493200; FYE 9/30/2022 Q3: 2493200; FYE 9/30/2022 Q4: 2493200; FYE 9/30/2023 Q1: 2493200
Consulting 5002
Equipment 5010
Equipment 5008
Other Direct Costs 5009
Material 5003
Sub K Overhead 5992
Sub K Overhead 5993
| G&A 5991 | FYE 9/30/2020 Q4: 41537.27; FYE 9/30/2021 Q1: 41537.27; FYE 9/30/2021 Q2: 41537.27; FYE 9/30/2021 Q3: 41537.27; FYE 9/30/2021 Q4: 41537.27; FYE 9/30/2022 Q1: 41537.27; FYE 9/30/2022 Q2: 41537.27; FYE 9/30/2022 Q3: 41537.27; FYE 9/30/2022 Q4: 41537.27; FYE 9/30/2023 Q1: 41537.27
BUDGETED Total
CONTRACTING | Committed | FYE 9/30/2020 Q4: 27100000
| Obligated | FYE 9/30/2020 Q4: 27100000
| Expended | FYE 9/30/2021 Q1: 5500000; FYE 9/30/2021 Q2: 21600000
Remaining Cash
| Q1 FY20 | Q2 FY20 | Q3 FY20 | Q4 FY20 | Q1 FY21 | Q2 FY21 | Q3 FY21 | Q4 FY21 | Q1 FY22 | Q2 FY22 | Q3 FY22 | Q4 FY22 | Q1 FY23 | Q2 FY23 | Q3 FY23 | Q4 FY23 | Q1 FY24 | Q2 FY24 | Q3 FY24 | Q4 FY24 | Q1 FY25 | Q2 FY25 | Q3 FY25 | Q4 FY25 | Q1 FY26 | Q2 FY26 | Q3 FY26 | Q4 FY26
Total Committed
Total Obligated
Total Expended
Budgeted Plan
Actual